	
	I year
	II year
	III year

	
	2012
	2013
	2014
	2015

	
	1
O
	2 
N
	3

D
	4

J
	5

F
	6

M
	7

A
	8

M
	9

J
	10

J
	11

A
	12

S
	13

O
	14

N
	15

D
	16

J
	17

F
	18

M
	19

A
	20

M
	21

J
	22

J
	23

A
	24

S
	25

O
	26

N
	27

D
	28

J

	WP 1
P1
	MANAGEMENT
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Set up
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	I coord meeting (Barcelona)
	
	15
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Report I coord meeting
P3
	
	30
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	II coord meeting 

(Madrid?)
	
	
	
	
	
	
	
	
	6
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Report II coord meeting

P3
	
	
	
	
	
	
	
	
	20
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Midterm report EACEA   (P1)
	
	
	
	
	
	
	
	
	
	
	
	
	31
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	III coord meeting (Budapest?)
	
	
	
	
	
	
	
	
	
	
	
	
	
	21
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Report II coord meeting

P3
	
	
	
	
	
	
	
	
	
	
	
	
	
	29
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	VI coord meeting 
(?)
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	5
	
	
	
	
	
	
	

	
	Report IV coord meeting

P3
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	25
	
	
	
	
	
	
	

	
	Final coord meeting (Roma)
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	16
	
	
	
	

	
	Final coord meeting report 
P3
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	31
	
	
	
	

	
	Final report  EACEA

(P1)
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	Marz 2015

	WP 2
	Preparation of resources and tools for Focus Groups
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Questions grid 

	
	
	18
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Observation grid
	
	
	
	11

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Guidelines
	
	
	
	31

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	WP 3
P4
	INV Focus Group
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	National Focus Groups 
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Report on National Focus Groups
	
	
	
	
	
	
	10


	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Final report “Define the Essential”
	
	
	
	
	
	
	
	31
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	WP4
P1 
	Pedagogical Model INV
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Researcher/trainers meeting on Pedag. Model
	
	
	
	
	
	
	
	
	6
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Meeting report

	
	
	
	
	
	
	
	
	20
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Pedagogical Model handbook
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	20
	
	
	
	

	WP

5
P1


	INV Training Path 
	
	
	
	
	
	
	 
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Training of trainers
	
	
	
	
	
	
	
	
	
	
	
	
	
	29

	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Training Path handbook
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	20
	
	
	
	

	WP 6
P2 
	Training Testing
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	National workshop


	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	On-line workshop


	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Training testing evaluation


	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Final workshop
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Training Workshop report 

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	23
	
	
	
	

	
	CD ROM
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	23

	
	
	
	

	WP 7
P2 
	Evaluation
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Planning
	
	
	
	
	
	
	
	29
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	INV  Midterm report
	
	
	
	
	
	
	
	
	
	
	
	
	4
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	INV Final report
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	20

	WP 8

P3
	Dissemination
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Planning
	
	15
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Web site
	
	
	
	18
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Thematic Workshop 
	
	
	
	
	
	
	
	
	
	
	
	
	21
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Workshop report
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	WP 9
	Exploitation
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	Public event 
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	
	30
	
	
	

	
	
	1 O
	2 
N
	3

D
	4

J
	5

F
	6

M
	7

A
	8

M
	9

J
	10

J
	11

A
	12

S
	13

O
	14

N
	15

D
	16

J
	17

F
	18

M
	19

A
	20

M
	21

J
	22

J
	23

A
	24

S
	25

O
	26

N
	27

D
	28

J

	
	
	2012
	2013
	2014
	2015


